Ceding Automation

Test Plan Discussion Pack

Furnley House Financial Planning Partners

Prepared by: Revathy S  |  Date: 22 May 2026

Purpose: This pack covers the IT-side responses to the six questions raised for the Functional Test (FT) and User Acceptance Test (UAT) discussion, plus a worked-example library of test scripts for each functional area in scope.

Audience: PMO, business sponsors (Lee, Natalie, Daniel), QA, dev leads (Nishant, Srinath), and UAT user group.

# 1. Context & key dates

| Milestone | Date | Owner |
| --- | --- | --- |
| Code freeze | 1 Jun 2026 | Dev leads |
| NFR-04 AI accuracy gate (≥85% HIGH-confidence, 50+ PDFs, 6+ providers) | ≤ 1 Jun 2026 | Nishant |
| Functional Test (Internal) — Chennai CA team | 1 – 7 Jun 2026 | Revathy |
| UAT — 5 business users | 8 – 15 Jun 2026 | Revathy + Natalie |
| Production launch | 16 – 17 Jun 2026 | Daniel + Revathy |
| Hypercare (10 working days) | 16 – 27 Jun 2026 | Dev + Revathy |
| Success review meet | 1 Jul 2026 | Lee + SLT |

## Scope reminder

- In scope (Phase 1): Pension, ISA, GIA

- Out of scope (Phase 2+): Bond, Final Salary / DB, Protection, EIS/VCT, Suitability Report automation, FE fundinfo, Fact Find, Origo API

- Hard gates: GDPR sign-off (TR-09) before live data; ≥85% HIGH-confidence AI extraction (NFR-04) before UAT

# 2. Functional Test vs UAT — what each is for

| Dimension | Functional Test (FT) | UAT |
| --- | --- | --- |
| Goal | Confirm the system behaves as specified against FR/TR/NFR. | Confirm the system supports the real ceding workflow end-to-end. |
| Run by | IT / QA + Chennai CA team | 5 business users (CA, Adviser/PP, Admin) |
| Data | Synthetic dummy clients + anonymised PDFs | Synthetic dummy clients + anonymised PDFs (NOT live until TR-09 cleared) |
| Window | 1 – 7 Jun 2026 | 8 – 15 Jun 2026 |
| Pass bar | Every Must FR has at least one PASS; no Sev1/2 open; NFR-02, NFR-06 met | All UAT users sign off their assigned scenarios; no Sev1/2 open |
| Output | FT exit report → gate for UAT entry | UAT sign-off → gate for go-live |

# 3. What's needed for FT & UAT

| # | Asset | FT | UAT | Owner |
| --- | --- | --- | --- | --- |
| 1 | Test environment — isolated Azure stack (App Service slot, dedicated Postgres, Azure Blob, Azure OpenAI test key) | Yes | Yes | Srinath (DevOps) |
| 2 | Test Zoho tenant / sandbox — CRM webhook, WorkDrive, deep-link, SSO | Yes | Yes | Revathy |
| 3 | Test RingCentral + Palindrome sandbox credentials (TR-05) | Yes | Yes | Revathy + Nishant |
| 4 | Dummy clients — 30–40 synthetic records covering Pension (all sub-types), ISA, GIA, plus On-Hold + missing-policy edge cases | Yes | Yes | Revathy + Natalie |
| 5 | Provider PDF corpus — 50+ anonymised PDFs across 6+ providers, mix of HIGH/MED/LOW | Yes | Yes | Nishant |
| 6 | Provider Directory test load — Aruna's verified file (Q-06/Q-07 must be unblocked first) | Yes | Yes | Aruna → Srinath |
| 7 | User accounts in each RBAC role — CA_TEAM, ADVISER, PARAPLANNER, ADMIN | Yes | Yes | Revathy |
| 8 | Test data reset script — rerun scenarios cleanly | Yes | Yes | Srinath |
| 9 | Test scripts / scenario packs (Section 7 of this doc) | Yes | Yes | Revathy + QA |
| 10 | Tester guidance pack — login, bug-raising, scope, known limitations | — | Yes | Revathy |
| 11 | UAT training session — prove NFR-05 (≤10 min training) | — | Yes | Revathy + Natalie |
| 12 | NFR-04 AI accuracy benchmark report — entry gate for UAT | Gate | Pre-req | Nishant |
| 13 | GDPR sign-off (TR-09) | — | Required before live data only | Security + SLT |
| 14 | Performance baseline — page load <3s UK + Chennai (NFR-02), 20 concurrent users (NFR-06) | Yes | — | Srinath |
| 15 | Defect log / triage board (see Sections 5–6) | Yes | Yes | Revathy |
| 16 | Daily 15-min defect triage standup during UAT | — | Yes | Revathy |
| 17 | Entry & exit criteria signed off in writing | Yes | Yes | Revathy → Daniel |

# 4. UAT high-level approach — per-tester scope

Recommendation: do NOT make every UAT person test every requirement. Slice by role and plan type so coverage mirrors how the system will actually be used.

## 4.1 Role split for 5 UAT users

- 2 × CA Team — data entry, checklist editing, document upload, call-script generation (heaviest workflow)

- 2 × Adviser / Paraplanner — review, approve, request-review, WorkDrive export

- 1 × Admin — provider directory, user management, RBAC

## 4.2 Plan-type coverage matrix

- Every Phase 1 plan (Pension / ISA / GIA) covered by at least 2 testers.

- Pension sub-types (per open Q-24) spread across CA testers — each tester takes 1–2 sub-types.

## 4.3 Shared scenarios all testers must run

- Zoho task → case auto-create (TR-04)

- Microsoft SSO login (TR-02)

- WorkDrive export of approved case (FR-17, TR-06)

- Audit trail visibility (FR-05)

## 4.4 End-to-end "golden path"

Each tester runs the full 10-stage flow on at least 1 case to catch handoff defects between stages.

## 4.5 UAT exit criteria

- Every Must FR has at least 1 PASS from each relevant role

- Zero open Sev 1 or Sev 2 defects

- NFR-02 (page load <3s) and NFR-06 (20 concurrent users) met

- All 5 UAT users sign their UAT exit form

# 5. Defect reporting channel

Single channel only. No Slack / email / WhatsApp bug reports — they get lost and are not auditable.

## 5.1 Recommendation: Zoho Desk → ceding-uat queue, with a fixed bug template

- Already inside Furnley House Zoho ecosystem — no new login for business users.

- MCP integration exists between Zoho Desk and Zoho Sprints — triaged bugs auto-mirror as items in the Ceding Automation Sprints project.

- Native attachments (screenshots / screen recordings), comment history, full audit trail.

## 5.2 Mandatory bug template fields

| Field | Description | Example |
| --- | --- | --- |
| Title | Short, specific, in plain English | ISA case checklist does not show ISA wrapper field |
| Test type | FT or UAT | UAT |
| Severity | Sev1 (blocker) → Sev4 (cosmetic) | Sev2 |
| Role used | RBAC role logged in as | CA_TEAM |
| Plan type + Case ID | Phase 1 plan + ID from app | ISA / Case CA-0042 |
| Steps to reproduce | Numbered, repeatable | 1. Log in 2. Open CA-0042 3. ... |
| Expected | What should happen per spec | Wrapper field should show "S&S ISA" |
| Actual | What did happen | Wrapper field is blank |
| Evidence | Screenshot / screen recording / link | screenshot.png |
| Environment | Browser + device | Chrome 124 / Win 11 |

## 5.3 Severity definitions & SLAs

| Severity | Definition | Target SLA |
| --- | --- | --- |
| Sev1 — Blocker | System down, data loss risk, security exposure, or core workflow cannot be completed by any user. | Fix in day |
| Sev2 — Critical | Core function broken for some users / plan types; workaround painful or impossible. | Fix in sprint |
| Sev3 — Major | Non-core function broken or significant UX defect; workaround available. | Backlogged with date |
| Sev4 — Minor / Cosmetic | Typo, alignment, label, non-impactful UX nit. | Backlogged |

# 6. Defect tracking, monitoring & reporting

- Single Kanban view in Zoho Sprints filtered to tag:bug across the active sprint — columns: Triage → In Dev → In Test → Done → Won't Fix.

- Daily 15-min triage standup during UAT — Revathy chairs; dev leads + business lead attend; each new ticket gets severity, owner, ETA.

- Daily UAT bug burn-down report auto-generated from Zoho Sprints, emailed 17:00 to Lee, Natalie, Daniel, SLT — open count by severity, age, trend, blockers.

- Weekly SLT summary for the BR-06 reporting commitment — defects raised / fixed / deferred, plus AI accuracy + throughput metrics.

- Live exit-criteria dashboard — open Sev1/2 count, % FRs passed, NFR-02/06 status. Go/no-go is data-driven.

## 6.1 Ownership

| Responsibility | Owner | Support |
| --- | --- | --- |
| Triage chair + daily report | Revathy | Dev leads |
| Severity definitions + SLA enforcement | Revathy + Nishant | — |
| Business prioritisation tie-breakers | Lee + Natalie | Daniel |
| AI / backend defect fixes | Nishant | Backend dev |
| Infra / DB defect fixes | Srinath | DevOps |
| UI / frontend defect fixes | Frontend dev | Revathy |
| Weekly SLT report compilation | Revathy | Daniel reviews |

# 7. IT-side work to start this week (T-10 days to FT, T-17 to UAT)

- Provision the test environment — separate Azure resource group, Postgres, Blob, App Service slot. Owner: Srinath.

- Stand up Zoho test tenant + RingCentral / Palindrome sandbox credentials. Owner: Revathy + Nishant.

- Build the 30–40 dummy client dataset and load into test Zoho CRM. Owner: Revathy + business lead.

- Draft the bug template + severity matrix, circulate to Lee / Natalie for approval. Owner: Revathy.

- Draft UAT test-script skeleton — one per Must FR, grouped by user journey (see Section 8). Owner: Revathy + QA, dev review.

- Confirm NFR-04 gate on track — Nishant to confirm the 50+ PDF / 6+ provider benchmark lands before 1 Jun.

- Confirm Aruna's Provider Directory delivery date — without it Q-06/Q-07 stay RED and FR-19/FR-23 cannot be tested.

- Schedule the UAT user training session — ideally 5 Jun, before UAT starts on 8 Jun. Owner: Revathy + Natalie.

- Update the Zoho Projects "Launch / Go live" task date from 10 Jun to 16/17 Jun (current mismatch). Owner: Revathy.

- Confirm GDPR pack (TR-09) progress with security lead — UAT can run on synthetic data, but go-live is blocked.

# 8. Test scripts — what they are and worked examples

## 8.1 What is a test script?

A test script is a single, repeatable instruction sheet a tester follows to verify ONE specific behaviour. It is not a list of features and it is not a tick-box. It tells the tester exactly what to do, what to expect, and how to record the outcome — so that two different testers running the same script get the same answer.

### Every test script has:

- Script ID — unique reference (e.g. TS-FR-03-01)

- Linked requirement(s) — the FR / TR / NFR being verified

- Tester role — which RBAC role the tester logs in as

- Pre-conditions — what state the system must be in before starting

- Test data — the specific case ID / PDF / Zoho task being used

- Steps — numbered actions, one action per step

- Expected result per step — what the tester should see after each action

- Overall expected outcome — the requirement-level result if all steps pass

- Evidence to capture — screenshots, exported file, audit-trail entry

- Result fields — PASS / FAIL / BLOCKED, defect reference, tester, date

### How test scripts map to FT vs UAT

- FT scripts — narrow, one per FR/TR/NFR; verify the spec line by line. Heavy on edge cases.

- UAT scripts — broader, journey-based; verify a real business outcome end-to-end (e.g. "process one ISA ceding case from Zoho task to WorkDrive export").

### Naming convention

TS-{FR|TR|NFR}-{number}-{sequence}. Example: TS-FR-10-02 = second test script for FR-10 (AI extraction).

## 8.2 Worked test-script examples per functional area

The examples below are illustrative — they cover the spine of Phase 1. Full library to be authored in Section 7, step 5.

### TS-FR-03-01 — Case auto-creates when Zoho blueprint task hits the ceding stage

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-03, TR-04 |
| Tester Role | CA_TEAM (observer); webhook triggers as SYSTEM |
| Pre-conditions | Test Zoho tenant connected to ceding app; webhook secret configured; user has CA_TEAM role. |
| Test Data | Synthetic Zoho task Z-TEST-001, plan type = Pension, client = TEST-CLIENT-01, provider group = Aviva. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | In test Zoho CRM, move Z-TEST-001 into the "Ceding — Ready for processing" blueprint stage. | Zoho task transition saves successfully. |
| 2 | Within 30 seconds, refresh the ceding app dashboard. | A new case appears, status = New, linked to Z-TEST-001. |
| 3 | Open the new case. | Client name, plan type (Pension), provider (Aviva), assigned-to (Zoho task owner) all match Zoho. |
| 4 | Check audit trail. | Entry recorded: action = CASE_CREATED, source = ZOHO_WEBHOOK, user = SYSTEM. |

Overall expected outcome: Case is created automatically in the app with all linked-fields populated from Zoho and an audit row written.

Evidence to capture: Screenshot of dashboard before/after; screenshot of audit trail row.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-FR-10-01 — Upload a single Pension PDF and AI extraction populates the checklist with confidence flags

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-06, FR-08, FR-10, FR-11, FR-12, NFR-01 |
| Tester Role | CA_TEAM |
| Pre-conditions | Case CA-TEST-PENSION-01 exists in status "Awaiting documents"; Azure OpenAI test key live; AI service healthy. |
| Test Data | Anonymised provider PDF AVIVA-PENSION-CLEAN-001.pdf (8 pages, known to extract HIGH on the benchmark set). |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Open CA-TEST-PENSION-01 → Documents tab → Upload. | File picker opens; PDF accepted; upload progress shown. |
| 2 | Wait for AI extraction to complete (max 2 min per NFR-01). | Progress indicator runs; case status auto-changes to "AI extracted"; total time recorded ≤ 120s. |
| 3 | Open the Checklist tab. | Pension-specific fields populated (policy number, transfer value, scheme name, etc.). ISA/GIA-only fields are NOT shown (FR-12). |
| 4 | Hover over each extracted field. | Source citation tooltip shows file name + page + section heading (FR-08). |
| 5 | Inspect the summary panel. | HIGH / MEDIUM-LOW / MISSING counts match the field-level confidence chips (FR-14). |

Overall expected outcome: Extraction completes <2 min, populates only plan-relevant fields, each with confidence + source citation, and the summary panel matches.

Evidence to capture: Timing screenshot, populated checklist screenshot, source-citation tooltip screenshot.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-FR-10-02 — Upload a second PDF to the same case — extraction re-runs and merges, confidence updates

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-07, FR-11 |
| Tester Role | CA_TEAM |
| Pre-conditions | CA-TEST-PENSION-01 has had AVIVA-PENSION-CLEAN-001.pdf already extracted (script TS-FR-10-01 PASS). |
| Test Data | Second PDF AVIVA-PENSION-SUPPLEMENT-001.pdf containing additional info (e.g. fund split). |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Upload second PDF to the same case. | Extraction kicks off again; status returns to "AI extracting". |
| 2 | Wait for completion. | Fund split fields populate; previously-MISSING fields move to HIGH/MEDIUM; previously-HIGH fields are preserved (no regression). |
| 3 | Check source citations on updated fields. | Citations now show whichever PDF supplied the most-confident value. |
| 4 | Check audit trail. | Entries recorded: DOCUMENT_UPLOADED + AI_RE_EXTRACTED + FIELD_UPDATED per changed field with old/new values. |

Overall expected outcome: Multi-document extraction merges cleanly and audit trail captures every field change.

Evidence to capture: Screenshot of summary-panel counts before/after; audit-trail export.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-FR-13-01 — CA team edits a low-confidence field manually; manual flag is set and both values stored

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-13, FR-05 |
| Tester Role | CA_TEAM |
| Pre-conditions | Case has at least one LOW-confidence field (e.g. transfer value) |
| Test Data | Field = transfer_value; AI extracted £12,450 LOW; correct value per source = £12,540. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Click Edit on the transfer_value field. | Inline editor opens; original AI value visible. |
| 2 | Change value to £12,540 and Save. | Field accepts input; confidence chip changes to MANUAL. |
| 3 | Hover the MANUAL chip. | Tooltip shows: "Original AI value: £12,450 (LOW). Manually edited by [User], [Timestamp]." |
| 4 | Open audit trail. | Row recorded: action = FIELD_EDITED, oldValue = £12,450, newValue = £12,540, source = MANUAL, user = test-ca@... |

Overall expected outcome: Manual edit overrides AI value, original is preserved, audit row is immutable.

Evidence to capture: Tooltip screenshot, audit row screenshot.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-FR-15-01 — CA marks case Ready for Review → paraplanner Zoho task created → paraplanner approves → WorkDrive export fires

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-15, FR-16, FR-17, TR-06 |
| Tester Role | CA_TEAM, then PARAPLANNER |
| Pre-conditions | Case CA-TEST-ISA-01 has 100% of Must fields HIGH or MANUAL; WorkDrive test folder configured. |
| Test Data | Case CA-TEST-ISA-01; paraplanner user = pp-test@...; WorkDrive folder = /UAT/TEST-CLIENT/Deal WIP. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Logged in as CA, click Mark Ready for Review on the case. | Status changes to "In review"; confirmation toast shown; a Zoho task is created for the paraplanner with a deep-link to the case. |
| 2 | Open the paraplanner's test Zoho dashboard. | New task visible, title contains client name, contains deep link to CA-TEST-ISA-01. |
| 3 | Log out, log in as PARAPLANNER, click the deep link in the Zoho task. | Lands directly on CA-TEST-ISA-01 in the app (SSO works, RBAC allows view+approve). |
| 4 | Click Approve on the case. | Status changes to "Approved"; confirmation toast shown. |
| 5 | Within 60 s, check the configured WorkDrive folder. | An .xlsx exists named per the convention; opens cleanly and contains checklist + audit trail tabs. |
| 6 | Open the audit trail in-app. | Entries recorded: STATUS_CHANGED (Ready for Review), ZOHO_TASK_CREATED, STATUS_CHANGED (Approved), WORKDRIVE_EXPORTED. |

Overall expected outcome: End-to-end approval-to-export chain works without manual intervention.

Evidence to capture: Screenshots at each step; the exported .xlsx file.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-FR-18-01 — App generates a call script for missing / low-confidence fields with correct provider routing

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-18, FR-19 |
| Tester Role | CA_TEAM |
| Pre-conditions | Case has ≥3 MISSING or LOW-confidence fields; Provider Directory loaded with Aviva entry including dept routing. |
| Test Data | Case CA-TEST-PENSION-02; provider Aviva; policy ref prefix "P-". |
| Notes | Depends on Q-07 (policy-ref prefix routing) being unblocked. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Open the case → Call Assist tab. | List of missing/low fields shown; button "Generate call script" enabled. |
| 2 | Click Generate. | Script generated within 10 s; displays provider name, correct phone number, correct dept (per prefix "P-"), and a numbered question list covering only the missing/low fields. |
| 3 | Inspect the question list. | Questions are plain-English, fields-mapped (not field IDs), and ordered by field importance. |

Overall expected outcome: Call script is correct, routed to right dept per provider/prefix, and contains only the relevant questions.

Evidence to capture: Screenshot of generated script.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-FR-20-01 — Post-call transcript ingested via Palindrome auto-fills the missing fields, tagged transcript-source

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-20, TR-05, TR-11 |
| Tester Role | CA_TEAM |
| Pre-conditions | RingCentral test recording exists for the case; Palindrome sandbox responsive. |
| Test Data | Recording ID RC-TEST-001 linked to CA-TEST-PENSION-02. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | On the case, click "Import call recording". | Recording fetched; Palindrome transcription job kicks off. |
| 2 | Wait for transcription + extraction (timeout: 3 min). | Previously-MISSING fields populate; each carries a TRANSCRIPT confidence/source tag. |
| 3 | Hover a transcript-sourced field. | Tooltip shows transcript excerpt + timestamp. |
| 4 | Audit trail check. | CALL_INGESTED + FIELD_UPDATED rows with source = TRANSCRIPT. |

Overall expected outcome: Call recording reduces case to 1 provider call (BR-03 target) and clearly distinguishes transcript-sourced vs PDF-sourced data.

Evidence to capture: Transcript excerpt tooltip + audit trail.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-FR-05-01 — Audit trail is complete and immutable across a full case lifecycle

| Field | Value |
| --- | --- |
| Linked Requirement(s) | FR-05, BR-04 |
| Tester Role | ADMIN |
| Pre-conditions | Case CA-TEST-ISA-01 has been taken end-to-end (use script TS-FR-15-01). |
| Test Data | Case CA-TEST-ISA-01. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Open case → Audit tab. | Chronological list of every state-changing action: CASE_CREATED, DOCUMENT_UPLOADED, AI_EXTRACTED, FIELD_EDITED (×N), STATUS_CHANGED (×N), ZOHO_TASK_CREATED, WORKDRIVE_EXPORTED. |
| 2 | Attempt to delete or edit an audit row via the UI. | No UI affordance to edit/delete; rows are read-only. |
| 3 | Attempt to DELETE / UPDATE on the audit_logs table directly (admin DB user). | Operation refused or logged separately (Prisma model should reject mutation on the audit table). |
| 4 | Export the audit trail. | CSV/Excel download contains every row with user, timestamp, action, old, new, source. |

Overall expected outcome: Every state change is captured, ordered, attributable, and tamper-proof.

Evidence to capture: Audit export.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-TR-02-01 — SSO from Zoho into ceding app — single sign, role auto-provisioned

| Field | Value |
| --- | --- |
| Linked Requirement(s) | TR-02, TR-07 |
| Tester Role | New user (not yet in app DB) |
| Pre-conditions | Azure AD test tenant has user new-test@furnleyhouse.co.uk; no record in the app's users table. |
| Test Data | Test Azure AD user. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | From Zoho dashboard, click the ceding-app launcher. | Redirects to Microsoft login; SSO completes without manual password entry. |
| 2 | Land in the ceding app. | User session active; role = CA_TEAM (auto-provisioned default). |
| 3 | Check users table as admin. | New row exists with the user's email + CA_TEAM role. |

Overall expected outcome: SSO works first-time, default role applied, no manual provisioning needed.

Evidence to capture: Network trace of OIDC handshake + screenshot of user row.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-TR-07-01 — RBAC — CA cannot approve, Adviser/PP cannot edit checklist, Admin cannot demote self

| Field | Value |
| --- | --- |
| Linked Requirement(s) | TR-07 |
| Tester Role | Three roles in sequence |
| Pre-conditions | One test user per role exists. |
| Test Data | Case CA-TEST-PENSION-03 in status "In review". |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Logged in as CA_TEAM, attempt to click Approve. | Approve button hidden or disabled; direct API call returns 403. |
| 2 | Logged in as ADVISER, attempt to inline-edit a checklist field. | Field is read-only; direct API call returns 403; Comment + Request Review controls visible. |
| 3 | Logged in as ADMIN (current user), attempt to change own role to CA_TEAM in the Users admin panel. | UI prevents action with toast ("You cannot demote your own account"); direct API call returns 400. |

Overall expected outcome: RBAC enforced both in UI and at the API layer.

Evidence to capture: Screenshot of each failure + DevTools network response.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-NFR-02-01 — Page load <3 s on 10 Mbps connection from UK and Chennai

| Field | Value |
| --- | --- |
| Linked Requirement(s) | NFR-02 |
| Tester Role | CA_TEAM |
| Pre-conditions | Test env deployed to prod-equivalent Azure region; 50 cases seeded. |
| Test Data | Browser DevTools network throttling = Fast 3G OFF / cable 10 Mbps; clear cache. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | From UK office, open the case dashboard with cleared cache. | DOMContentLoaded < 3 s; Largest Contentful Paint < 3 s. |
| 2 | Open a case detail page. | LCP < 3 s. |
| 3 | Repeat from Chennai office (or VPN-routed Chennai test node). | Both pages still < 3 s. |

Overall expected outcome: Page-load SLA met for both geographies.

Evidence to capture: Lighthouse / WebPageTest export from each location.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-NFR-04-01 — AI accuracy gate — ≥85% of fields HIGH-confidence across the benchmark corpus

| Field | Value |
| --- | --- |
| Linked Requirement(s) | NFR-04 |
| Tester Role | AI lead (Nishant) + QA observer |
| Pre-conditions | Benchmark corpus of 50+ PDFs across 6+ providers staged; ground-truth answer keys prepared. |
| Test Data | Full benchmark PDF set. |
| Notes | If gate fails, UAT slips — escalate to Lee + Daniel same day. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Run the benchmark script against the AI extraction service. | Per-PDF results recorded; per-field confidence captured. |
| 2 | Aggregate: count of fields by confidence band per provider and overall. | Report produced with ≥85% HIGH overall AND no single provider <70% HIGH. |
| 3 | Capture failure cases (LOW or wrong). | Failure log captured; flagged to AI lead for retraining if needed before next run. |

Overall expected outcome: NFR-04 gate cleared; this is the entry condition for UAT.

Evidence to capture: Benchmark report + per-provider table.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

### TS-NFR-06-01 — 20 concurrent Chennai CA users without performance degradation

| Field | Value |
| --- | --- |
| Linked Requirement(s) | NFR-06 |
| Tester Role | DevOps + QA |
| Pre-conditions | Test env deployed; load test tool (k6 or similar) configured against test env URL. |
| Test Data | Script simulating 20 concurrent users running: log in, open dashboard, open a case, upload a small PDF. |

Steps & expected results

| # | Action | Expected result |
| --- | --- | --- |
| 1 | Run baseline with 1 user. | Capture p50, p95 page load + extraction time. |
| 2 | Ramp to 20 concurrent users sustained for 10 min. | p95 page load stays < 4 s; AI extraction stays < 150 s; no 5xx; CPU < 80% on backend. |
| 3 | Inspect Application Insights during the run. | No error spikes; no thread pool starvation. |

Overall expected outcome: System sustains 20 concurrent users with acceptable degradation; capacity for the Chennai team confirmed.

Evidence to capture: Load-test report + AppInsights dashboard screenshot.

Result: PASS / FAIL / BLOCKED  |  Defect Ref: __________  |  Tester: __________  |  Date: __________

## 8.3 What the full library should cover

From the above pattern, the complete FT script library should contain at minimum one script per Must FR/TR/NFR in scope. The table below shows the target distribution.

| Area | Requirement(s) | Approx. # FT scripts | Notes |
| --- | --- | --- | --- |
| Case Management | FR-01 to FR-05, FR-25 | 8 | Includes On-Hold and missing-policy paths. |
| Document Ingest | FR-06 to FR-09, FR-27 | 5 | Includes Origo manual upload path. |
| AI Extraction | FR-10 to FR-12, NFR-01, NFR-04 | 6 | Per-plan-type scripts (Pension, ISA, GIA). |
| Checklist + Approval | FR-13 to FR-17 | 6 | Includes RBAC negative cases. |
| Call Assist + Transcript | FR-18 to FR-20, TR-05 | 5 | Depends on Palindrome sandbox. |
| LOA + Provider Directory | FR-19, FR-21 to FR-23, TR-13 | 4 | Depends on Aruna's directory. |
| Integrations — Zoho | TR-02, TR-03, TR-04, TR-06 | 5 | Includes deep-link, webhook, WorkDrive export. |
| Security + RBAC + Audit | FR-05, TR-07, TR-08, TR-10 | 5 | Includes self-demote, audit immutability. |
| Performance + Reliability | NFR-01, NFR-02, NFR-03, NFR-06 | 4 | Run from UK + Chennai. |

Approximate FT script total: 48. UAT scenario count: ~10 end-to-end journeys (1 per business outcome × 3 plan types + admin / on-hold / two-call edge cases).

# 9. Approval & next steps

- Confirm severity definitions + SLAs at the meeting.

- Agree the Zoho Desk → Zoho Sprints defect channel.

- Agree the per-role UAT slicing approach.

- Sign off the IT-side work list in Section 7.

- Authorise full test-script authoring (Section 8.3 table) — target completion 31 May 2026.